Thozhi Federation - Quarterly Report

Quarter: Q1

Reporting Period: April 1, 2025 – June 30, 2025

Date of Submission:  09.07.2025

Prepared by: Dharshini K P

Designation: Chief Executive Officer

Approved by: Mr. A. Saravanan

Designation: Secretary

1. Executive Summary

During this quarter, Thozhi Federation made significant progress in organizational strengthening, partnership building, and member engagement. A finalized strategic plan was developed to guide the Federation’s medium-term direction, aligning program priorities with both community needs and institutional growth. Additionally, multiple project-related document including concept notes and a detailed pitch note were prepared to explore collaborative opportunities with government departments and other institutional partners.

Efforts to increase visibility and diversify funding sources were actively pursued. The Federation successfully registered on 16 crowd funding and visibility platforms, with profile validation completed in 5. This marks a key milestone toward resource mobilization and building a broader supporter base for women-led community initiatives.

A major governance achievement this quarter was the Executive Committee (EC) meeting, which saw 100% attendance a clear indicator of the growing commitment among leadership. The meeting focused on future planning, collaboration strategy, and accountability mechanisms.

Thozhi Federation also received an official confirmation letter from the District Social Welfare Office (DSWO), Tirupattur, approving collaboration for future government-linked activities. This is a significant step toward mainstreaming the Federation's role in district-level development processes.

In preparation for capacity building, the Federation scheduled and conducted panel interviews for representatives of Member Organizations to select trainers for upcoming online member trainings. This process ensured transparency and merit-based selection of facilitators who will lead digital learning initiatives.

While progress has been commendable, challenges remain around the slow validation process on some digital platforms and the need for sustained government engagement across districts. However, the Federation is well-positioned to overcome these barriers with the current momentum and strategic clarity.

2. Organizational Overview

- Federation Name: Thozhi Federation

- Registered Address: 5,394/ Kamarajar nagar, Nallampalli, Dharmapuri

- Districts Covered: Dharmapuri

3. Programmatic Activities

| Program Name | Objective | Activities Conducted | Target Group | No. of Beneficiaries | Key Outcomes | Remarks |
| --- | --- | --- | --- | --- | --- | --- |
| District-wise Member Organization (MO) Visit/Meetings | To strengthen coordination and planning across MOs in different districts | Conducted structured review and planning meetings | CBO Representatives, EC Members | 45 | Improved communication between Federation and MOs; district-level activity plans finalized | High participation and proactive planning noted |
| May Day Sensitization Workshop on ICC for Women Worker Leaders at Tirupattur | To build awareness on Internal Complaints Committee (ICC) and prevention of sexual harassment at the workplace | One-day workshop with interactive sessions and legal orientation | Women Worker Leaders, CBO Members | 52 | Increased awareness on workplace safety and rights; leaders committed to forming ICCs locally | Strong interest from participants in follow-up legal training |
| Joint Consultation on Women Workers with CSOs at Dharmapuri | To facilitate collaboration between civil society organizations on issues related to women workers | Panel discussion, group sharing, and identification of priority issues | NGO Leaders, Trade Union Reps, Women Workers | 38 | Shared understanding developed on key issues affecting women workers; initial discussions held on future joint actions | No formal resolutions or legal follow-up initiated yet |
| Right to Health campaign | Planning for a campaign to advocate on passing Right to Health bill in Assembly. And Health Assembly | Participated at the consultation held at Trichy by Mr. Shankar | NGO and CSOs from 21 districts | 30 | District level Structure promoted during this period in | Health Assembly planned to conduct before Aug 2025. In collaboration with Health system |
| Promotion organic farming | To promote organic farming in Tamil Nadu | State level Conclave held at Madurai | Members from the 30 districts. | 540 | Targeted to promote 6000 ha | Organised by NABARD and IOB. |
| Dhwani 2 days Fundraising workshop | To build capacity on fundraising strategies and tools | Two-day practical training on fundraising frameworks and donor mapping | Federation Staff, MO Leaders | 35 | Enhanced understanding of donor engagement, proposal writing, and fundraising strategies | Positive feedback; follow-up plan for mentorship in fundraising |
| MNI meeting | To review and strengthen the activities of Makkal Nal Vazhvu Iyakkam and promote community participation in health governance | Review meeting with representatives from various districts to share updates, challenges, and plans; discussion on JASS Committee formation and PHC-level engagement | MNI District Representatives, Federation Team | 28 | Strengthened coordination and shared planning across MNI units; Initiated implementation of JASS Committees; Several members nominated and accepted as committee members in their respective PHCs | Increased grassroots health governance; Federation’s role in PHC-level accountability strengthened |
| DSWO visit | To strengthen linkage with Department of Social Welfare and Women Empowerment | Field visit and interaction with DSWO | Federation Team, MO EC Members | 07 | Strengthened rapport with district administration; support sought for schemes | DSWO assured future collaboration in awareness and outreach efforts |
| New CEO appointment | Transition in leadership | Official handover meeting and induction | Federation Staff, MO Leaders | 20 | Leadership transition completed smoothly; shared vision for 2025-28 developed | CEO committed to member-centric approach and transparency |
| TN COACH Fundraising workshop | To equip NGOs with knowledge on CSR and institutional fundraising | Participated in TN COACH organized session on CSR readiness | NGO Staff, Federation Leaders | 45 | Improved understanding on corporate partnerships and eligibility for CSR grants | Need to develop organizational brochure and compliance checklist |
| OMT Panel Interview | To finalize Participants for Organisational MemberTraining (OMT) | Conducted interviews and assessments of potential participants | Shortlisted TOT Candidates | 18 | Final list of trainers selected for rollout of OMT in member organizations | Focus on regional representation and experience-based selection |

4. Governance and Meetings

| Meeting Type | Date | Participants | Agenda Points | Decisions Taken / Action Points |
| --- | --- | --- | --- | --- |
| EC meeting | 31.05.2025 | All EC members 1. Saravanan 2. Saraswathi 3. Pathimaraj 4. Read Selvam 5. Kulandai Dass 6. Gunaseeli 7. Nagalakshmi 8. Jalaludhin 9. Seethalakshmi 10. Sekar 11.Radhakrishnan Secretariat Team: 1.Dharshini (CEO) 2.Shankar (MRP) 3.Jayavarshini (Admin) | 1. Last Quarterly Activity review. 2. Approval of Dhwani Fund training cost. 3. Strategic plan approval & concept note. 4. Enrollment in Finding Agency 5. Filing of Audit and 10BD 6. Filing of TAN 7. Registration in CSR 8. 2025 - 2026 plan 9. Online training 10. Members visit 11. Members Training 12. Membership fee 13. AGBM 14. Any other matter. | 1.Resource book 2.Society Renewal 3.POSH policy Complaints addressing 4.New member added 5.Revised Member Directory 6.Parameters discussion 7.Niranthara Lite program training 8.Compliance 9.Annual Plan and Budget 10.Strategy plan discussion 11.Members SAT score 12.Pitch Note & Concept note discussion |

5. Financial Summary

| Particulars | Opening Balance | Income (Sources) | Federation Contribution | Expenditure (Head-wise) | Closing Balance |
| --- | --- | --- | --- | --- | --- |
| Secretariat Grant Salary |  | ₹2,64,000 | ₹66,000 | ₹3,30,000 | ₹0.00 |
| Secretariat Grant Travel | - | ₹30,000 | ₹0.00 | ₹28,798 | ₹1,202 |
| Federation Programme Activity Expenses (EC meeting) | - | ₹60,000 | ₹7,500 | ₹10,000 | ₹57,500 |
| Grand Total | - | ₹3,54,000 | ₹73,500 | ₹3,68,798 | ₹58,702 |

6. Monitoring & Evaluation

Thozhi Federation implemented regular internal reviews and feedback from Dhwani Foundation, Board Members, Executive members and Member organizations to track progress across programmatic and organizational activities. Monitoring was carried out through weekly review meeting, EC meeting, monthly team check-ins, updates from member organizations, and review of key milestones, such as strategic plan finalization, digital platform registrations, and concept note development. A documentation tracker (Excel Sheet, Drive) was used to monitor submission of concept notes, project documents, and funding applications. Regular reporting to the Executive Committee (EC) and periodic updates shared with key stakeholders ensured transparency and accountability.

7. Challenges Faced

- Delayed Digital Platform Validations: Although registration on 16 crowd funding/visibility platforms was completed, validation on many platforms remains pending, slowing visibility and fundraising efforts.

- Limited Government Engagement in Some Districts: While significant collaboration was achieved with DSWO, Tirupattur, efforts to engage other districts are still in progress, requiring more sustained follow-up.

- Resource Mobilization Barriers: Although progress has been made, tangible financial support from new platforms or partners is yet to materialize.

8. Future Plans for Next Quarter

Capacity Building:

- Dhwani Foundation Visit – Mr. Ayyappan (July 2025)

- Conduct online Member training sessions led by newly selected trainers from member organizations. (July 2025)

- Dhvani Network and Thozhi Federation Joint effort on CSR and Digital visibility to Dharmapuri Dt. NGOs.

- Collaborative Effort with Govt. on ICC – Planning and initiate work together. ( July 2025

- Consultation with Union leaders/Facilitators for confirming parameters and online training plan for union representatives. (July 2025)

- Training for union representative on compliances, governance etc. (1st Week Aug 2025)

- Members Training on create visibility by digital platform (Sep 2025)

- Sub-Committee members training (Sep 2025)

- AGBM (2025)

9. Partnerships / Fundraising:

- Follow up with registered digital platforms to complete profile validation and initiate campaigns.

- Reach out to new institutional donors and CSR partners with the finalized pitch note and concept documents.

- Explore MoU’s with local government departments to deepen collaboration in new districts.

Thanks